Seattle-Tacoma International Airport Rules for Airport Construction

December 1, 2024

# CONTENTS

Contents

CONTENTS	2

ACRONYMS AND ABBREVIATIONS	5

1.	GENERAL INFORMATION	7

Introduction	7

Purpose and Scope	7

Tenant Improvement Projects	8

Amendment of These Rules	8

Administration and Enforcement of Guidelines	8

Appeal of Code Interpretations	9

Codes and Authorities	9

Safety	10

Damage to Airport	10

Access and Inspections	10

Equal Employment Opportunity Requirements	10

Acceptable Work Site	10

Prevailing Wages	11

Indemnification	11

Applications for Certification of Compliance of Port Standards	12

Roadway Systems	12

Federal Aviation Administration	12

3.	AIRPORT BUILDING DEPARTMENT	13

Codes and Authority	13

4.	FIRE DEPARTMENT	14

Introduction	14

Asbestos and Other Regulated Materials	15

6.	ENVIRONMENTAL	16

Introduction	16

National and State Environmental Policy Acts Requirements.	16

General Permit Compliance	16

Water Quality and Stormwater Management	17

Contaminated Soil and Groundwater Management	18

Hazardous Materials and Waste	18

Waste Disposal	19

Air Quality	19

Construction Waste Management	20

Critical or Sensitive Area Protection	20

Inspections	20

7.	AIRPORT OPERATIONS	21

Introduction	21

Coordination of Construction with Airport Operations	21

Federal Aviation Administration Notice of Proposed Construction or Alteration Requirements	21

Noise	21

Hazardous Wildlife Mitigation and Pest Prevention	21

Heat and Glare	22

Equipment Lighting	22

Vehicles in the Air Operations Area	22

2)	Operations	22

3)	Parking	22

Demolition and Construction	23

2)	Flagging	23

3)	Temporary Construction Barricades	23

4)	Protection	23

5)	Temporary Ceiling Removal	23

6)	Equipment in the Terminal	24

7)	Direct Digital Control System	24

8)	Utility Shutdown Impacts	24

Laydown Areas and Office Operations	24

1)	Stored Materials	24

Site Access, Deliveries, and Removal of Demolished Materials	25

1)	Deliveries and Removals	25

2)	Elevators and Hoistways	26

3)	Use of Lobbies and Concourses	26

4)	Construction Dumpsters	26

Work Hours, Holidays, Black-out Periods, and Other Time Restrictions	27

2)	Port Staff Holidays	27

3)	Construction Blackout Periods	27

4)	Other Specific Time Restrictions	27

8.	TRAFFIC AND LANDSIDE OPERATIONS	29

Introduction	29

General	29

Project Definition	29

9.	SECURITY	31

Introduction	31

Identification and Facility Access	31

2)	Keys	31

3)	Cores	31

Terminal Work	32

Perimeter Fencing	32

Restricted Areas	32

10.	CONSTRUCTION MANAGEMENT	33

Introduction	33

Notice to Proceed and Pre-Construction Meetings	33

Schedule Management and Coordination	33

Construction Coordination	33

1)	Construction Advisory Form	33

2)	Coordination Meetings	34

3)	Coordination with other Port Work	34

Pre-installation Meetings	34

Contractor Quality Control Program	34

Utility Shutdown Coordination: Heating, Ventilation, Air Conditioning, Plumbing, and Electrical Utility Systems	34

Construction Inspections	35

1)	Inspections	35

2)	Inspections Coordination	36

Electrical Room Access for Work or Work Requiring Electrical Shutdowns and/or Project Electrical Safety Meeting	37

Temporary Utility Connections	38

Project Close-Out	38

APPENDIX A — DEFINITIONS	40

APPENDIX B — DAILY PRE-HOT WORK CHECK LIST	45

Port of Seattle Fire Department Daily Pre-Hot Work Checklist	45

Required Precautions	45

Requirements 35’ from Hot Work	45

Hot Work on/in Closed Equipment, Ductwork and Piping	45

Hot Work on Ramp	45

Fire Watch/Fire Monitoring the Hot Work Area	46

Fire Watch Requirements and other Considerations	46

For questions or concerns about this document, contact Greg Carey at carey.g@portseattle.org

# ACRONYMS AND ABBREVIATIONS

See Appendix A for definitions

ABD	Airport Building Department

ACFM	Air Cargo Facilities Manager

ACM	asbestos-containing material

ADR	Airport Dining and Retail

A/E	Architect/Engineer

AED	automated external defibrillator

Airport	Seattle-Tacoma International Airport

AMA	Airport Movement Area

ANSI	American National Standards Institute

AOA	Airport Operations Area

ARC	Architectural Review Committee

AV	Aviation

AV/ENV	Aviation Environmental

AV/F&I	Aviation Facilities and Infrastructure AV/Maintenance	Aviation Maintenance

AV/OPS	Aviation Operations

AWWA	American Water Works Association

C of O	Certificate of Occupancy

CAD	computer-aided design

CIP	Capital Improvement Project

CM	Construction Manager

COPS	Application for Certification of Port Standards

CPL	Construction Program Leader

CPM	Capital Project Manager

CSR	Construction Support Representative

DCS	Document Control Specialist

DDC	Direct Digital Control

ENV	Environmental

- F	degrees Fahrenheit

F&I	Facilities and Infrastructure

FAA	Federal Aviation Administration

FOD	foreign object debris

gpm	gallons per minute

HVAC	heating, ventilation, and air conditioning

IBC	International Building Code

ICC	International Code Council

ID	identification

IFC	International Fire Code

ILA	Interlocal Agreement

IWTP	industrial wastewater treatment plan

L&I	Washington State Department of Labor and Industries

mph	miles per hour

MUST	Mechanical Utilities System Team

NEPA	National Environmental Policy Act

NFPA	National Fire Protection Association

NPDES	National Pollutant Discharge Elimination System

OPs	Operations

NTP	Notice to Proceed

PCS	Port Construction Services

PEST	Proactive Electrical Systems Team

PM	Project Manager

Port	Port of Seattle

Port FD	Port of Seattle Fire Department

psi	pounds per square inch

psig	pounds per square inch gauge

RAC	Rules for Airport Construction

RCW	Revised Code of Washington

RMM	Regulated Material Management

RPBA	reduced pressure backflow assembly

SDR	shutdown request

SEA	Seattle-Tacoma International Airport

SEPA	State Environmental Policy Act

SIDA	Security Identification Display Area

START	SeaTac Telecommunications Architecture Review Team

STIA	Seattle-Tacoma International Airport

TSA	Transportation Security Administration

UL	Underwriters Laboratories

UPC	Uniform Plumbing Code

WAC	Washington Administrative Code

# GENERAL INFORMATION

## Introduction

The Rules for Airport Construction (RAC) apply to all construction projects at Seattle-Tacoma International Airport (Airport) and properties associated with the Airport, whether implemented by the Port of Seattle (Port) or one of its tenants. The Port owns and operates the Airport (see Section 1.C., Tenant Improvement Projects, for additional information for tenant improvement projects).

## Purpose and Scope

The Port is committed to developing and maintaining safe, pleasant, and efficient facilities that meet all environmental requirements for the public and for people working in and adjacent to the Airport. This document provides guidance and direction in executing construction. Where this document is general rather than specific, Contractors will refer to specific project documents and adhere to standard practices, materials, and quality. If a Contractor believes there is a conflict or potential conflict between the RAC and its contract or any other project document, the Contractor must notify the Port of such conflict or potential conflict before the Contractor takes any action in reliance on such conflict or potential conflict. Contractor’s failure to do so shall constitute a waiver by the Contractor of any legal right to rely on such conflict or potential conflict.

These guidelines apply, within the legal boundaries of Airport and Port properties associated with the Airport, to the following:

  - Construction, alteration, repair, relocation, or demolition of any facility, its structure, exterior, or interior finishes

  - Filling or grading of land

  - Landscaping

  - Construction of pavement

  - Installation of water, storm drainage, sewer, and industrial waste lines

  - Power and control systems and other underground facilities

  - Installation of heating, ventilating, and air conditioning systems

  - Conveying and mechanical systems

  - Fire protection systems and facilities

  - Electrical power facilities and systems

  - Environmental protection systems

  - Communication systems, including wireless

  - Cleanup of soils and groundwater conducted under federal or state environmental regulations and aboveground and underground fuel storage and distribution facilities

Contractors working at the Airport interact with various Port departments, including project management, building, fire, construction management, construction safety, operations,

maintenance, environmental, and security. The RAC is organized by these disciplines to inform contractors how these departments facilitate and assist in completing construction projects at the Airport.

The Port is implementing electronic systems for design, permitting, and construction processes. Tenants, tenant designers, tenant vendors, and tenant contractors will use the platform(s) that the Port implements.

## Tenant Improvement Projects

Tenant improvement projects are required to comply with the requirements of Tenant’s lease, Tenant Improvement Design and Construction Process Manual, Tenant Improvement Construction General Requirements, and the Construction Safety Manual, along with Port standards, guidelines, rules, and regulations. If there is a conflict between a lease and this document, then the terms of the lease shall govern; provided however, that if a tenant believes there is a conflict or potential conflict between the RAC and tenant’s lease, tenant must notify the Port of such conflict or potential conflict before the tenant takes any action in reliance on such conflict or potential conflict. Tenant’s failure to do so shall constitute a waiver by the tenant of any legal right to rely on such conflict or potential conflict.

## Amendment of These Rules

The requirements set forth herein shall apply to all construction at the Airport and pertain to all contractors executing the work. To retain flexibility and permit the adoption of new techniques, criteria, procedures, any requirements herein may be revised by the Port without prior notice to enhance the overall facility safety and utility. Contractors are required to conform to all such amendments.

## Administration and Enforcement of Guidelines

These guidelines are to be administered and enforced by Port personnel as described within this manual. However, the requirements contained in these guidelines apply regardless of whether they are administered or enforced by Port personnel, and the failure of Port personnel to enforce any such requirements shall not be construed as a waiver or modification of any requirement. Any waiver or modification of any requirement contained in the guidelines must be in a writing signed by the Port and expressly state that a requirement contained herein is being waived or modified.  Following are key Port personnel interfaces with construction:

  - Construction Manager (CM)

  - Construction Inspector/Inspector

  - Construction Safety Manager

  - Project Manager (PM)

  - Port Construction Services (PCS)

  - Construction Program Leaders (CPL)

  - Construction Project Manager (CPM)

  - Aviation Operations (AV/OPS)

  - Construction Support Representatives (CSRs)

  - Airport Building Department (ABD) reviewers and inspectors

  - Aviation Maintenance (AV/Maintenance)

  - Aviation Facilities and Infrastructure (AV/F&I)

  - Port of Seattle Fire Department (Port FD)

  - Aviation Security (AVSEC)

  - Aviation Environmental (AV/ENV)

  - Erosion Control and Stormwater Technician (CM)

## Appeal of Code Interpretations

Appeals regarding code interpretations or the suitability of alternate materials shall be directed to the ABD.

## Codes and Authorities

All construction must meet the requirements of the most current edition of the following codes, Port standards, regulations, and resolutions in place at the start of construction:

  - Washington State Building Code per Revised Code of Washington (RCW) 19.27

  - Federal Aviation Administration (FAA) Requirements

  - Washington Industrial Safety and Health Act

  - Washington Administrative Codes (WAC)

  - Occupational Safety and Health Administration of the United States

  - U.S. Environmental Protection Agency

  - Washington State Department of Ecology

  - US. Department of Fish and Wildlife

  - U.S. Geological Survey

  - U.S. Army Corps of Engineers

  - National Fire Protection Association

  - Interlocal Agreement between the Port of Seattle and the City of SeaTac for projects located on Port-owned property within or facing the City of SeaTac

## Safety

No construction may be performed that is or may become dangerous to public health and safety. Contractors approached by Port project manager, construction manager, inspector, or construction safety managers about safety must take immediate action to address the identified concern(s). In case of emergency or immediate life safety issues, direction may be provided by other Port staff.

## Damage to Airport

The contractor is financially responsible for and must repair, to the satisfaction of the Port, all damage to existing Airport or third-party property, including (but not limited to) facility interior and exterior finishes, structure, pavement, roads, bridges, drainage pipelines, lighting system, grounds / natural resources, equipment and systems, or other Airport improvements impacted by its work, including such Port or third-party property that may also be contemporaneously under construction. When essential utilities or systems are damaged, repairs must be made immediately. The contractor is responsible and liable for all injury to persons and damage to property resulting from their operation.

If damage to such Airport or third-party property occurs, then the contractor must notify and coordinate with the Port Inspector, CM, PCS CPM, or PM before undertaking repairs. All associated costs incurred by the Port (including, but not limited to, soft costs) shall be reimbursed by the contractor.

If the Port determines, in its sole discretion, that any or all repairs should not be undertaken or performed by contractor, contractor shall be responsible for all costs incurred by the Port to perform the repair work with its own forces or to contract for such work, or any combination of the two, including Port soft costs associated with such work.

## Access and Inspections

The Port reserves the right to enter a construction project work zone or storage area(s) at any time to provide fire protection; ensure emergency and routine security; perform maintenance; perform safety, health, environmental, and construction inspections; and ensure conformance with Port rules, standards, and code requirements.

## Equal Employment Opportunity Requirements

For projects funded in whole or part by the Port or federal government, additional Equal Employment Opportunity requirements may apply. In those situations, the Port should be contacted for additional guidance.

## Acceptable Work Site

The Contractor shall ensure an Acceptable Work Site. Any behavior that demonstrates hostility related to race, gender or sexuality, inappropriate conduct or comments intended to harm another individual, and/or hostile or discriminatory actions against another individual are strictly prohibited.

## Prevailing Wages

Where required by law, contract, Tenant Reimbursement Agreement, or otherwise as directed by the Port, the contractor shall comply with Washington prevailing wage requirements (including but not limited to timely filing and submitting Intents and Affidavits) and pay prevailing wages.

## Indemnification

- The requirements of this Section N shall apply if there is no express indemnification provision contained in the lease, contract, or other written agreement with the Port that authorizes construction by a Contractor that is subject to the RAC; otherwise the express indemnification provision contained in the lease, contract, or other written agreement with the Port that authorizes construction by a Contractor shall apply.

- Contractor shall defend, indemnify and hold harmless the Port and its agents from all liability, claims, damages, losses and expenses, whether direct, indirect or consequential (including, but not limited to, attorneys' and consultants' fees and other expenses of litigation or arbitration) arising out of or relating to the construction of any project undertaken by Contractor at the Airport, which is caused, or alleged to be caused, in whole or in part, by Contractor (which for the purposes of Subparagraphs (2)), (3)), and (4)) of this Section only shall include the Contractor, and all of their Subcontractors, Sub-subcontractors, Suppliers, agents, any other person directly or indirectly employed by any of them, or anyone for whose acts any of them may be liable); provided, however, that where such liability, claim, damage, loss or expense arises from the concurrent negligence of (1) the Port or its agents, and (2) the Contractor, it is expressly agreed that the Contractor’s obligations of defense and indemnity under this Section shall be effective only to the extent of the Contractor’s negligence. Such obligations shall not be construed to negate, abridge, or otherwise reduce any other right or obligation of indemnity that would otherwise exist as to any person or entity described in this Section. This Section shall not be construed to require the Contractor to defend, indemnify, or hold harmless the Port from such claims, damages, losses, or expenses caused by or resulting from the sole negligence of the Port or its agents.

- In any and all claims against the Port or its agents by any employee of the Contractor, the indemnification obligation of Subparagraph (b) above shall not be limited in any way by any limitation on the amount or type of damages, compensation benefits payable by or for the Contractor under applicable workers' or workmen's compensation, benefit, or disability laws (including, but not limited to the Industrial Insurance laws, Title 51 of the Revised Code of Washington). The Contractor expressly waives (as to the Port only) any immunity the Contractor might have had under such laws, and, by requesting permission from the Port to construct and by actually constructing a project at the Airport, acknowledges that the foregoing waiver has been mutually negotiated by the parties.

- The Contractor shall pay all attorney's fees and expenses incurred by the Port in establishing and enforcing the Port's rights under this Section, whether or not suit was instituted.

2. DESIGN APPROVALS

- DESIGN APPROVALS

## Applications for Certification of Compliance of Port Standards

Prior to submitting to the authorities having jurisdiction for permits, the design and all required support documentation (i.e. applications for connection, calculations, etc.) must be reviewed for compliance with all Port rules, regulations, standards, and guidelines. A signed Application for Certification of Compliance of Port Standards form must be included with the permit submittal. A copy of the Certification of Compliance of Port Standards form may be obtained from the Port PM.

## Roadway Systems

Port Engineering approval of changes to Airport roadway systems is required.

## Federal Aviation Administration

Depending upon the scope and location at the Airport one or more separate FAA reviews of the project may be required. These reviews may include the following:

  - FAA Form 7460 review—This is required if the project will use a crane anywhere at the Airport, if it will alter the footprint of an existing terminal or building, or if a ‘temporary’ structure is being installed for longer than six months. Please note that 7460 reviews take a minimum of 90 calendar days for approval.

  - Contractor’s Safety Phasing Plan Review—If required, a Contractor’s Safety Phasing Plan can take 6 to 8 weeks for FAA review and approval.

  - National and State Environmental Policy Act (NEPA/SEPA) Environmental Review—If required, the NEPA/SEPA review and approval process can take 4 to 6 months.

  - The Port will coordinate reviews with the FAA.

# AIRPORT BUILDING DEPARTMENT

The City of SeaTac/Port of Seattle Interlocal Agreement (ILA) https://www.portseattle.org/sites/default/files/2020- 12/2018_Interlocal_Agreement_Signed_w_SeaTac.pdf

The ILA must be reviewed to determine the agency or agencies having authority over permitting and the applicable ILA development standards for the specific project location. The Port PM can assist with this review.

## Codes and Authority

The ABD is responsible for administering and enforcing the following applicable Washington State codes. The code cycle is determined by the vesting of the permit application:

    - International Building Code (IBC)

    - International Mechanical Code (IMC)

    - International Fuel Gas Code (IFGC)

    - Liquefied Fuel Gas Code (NFPA 58)

    - National Fuel Gas Code (NFPA 54 for LP gas installations only)

    - Uniform Plumbing Code (UPC)

    - International Energy Conservation Code (IECC, WSEC)

    - ICC/ANSI A117.1 Accessible and Usable Buildings and Facilities

    - International Fire Code (IFC)

    - National Electrical Code (NFPA 70) – Permitted and inspected by WA LNI

# FIRE DEPARTMENT

The City of SeaTac/Port of Seattle Interlocal Agreement (ILA) https://www.portseattle.org/sites/default/files/2020- 12/2018_Interlocal_Agreement_Signed_w_SeaTac.pdf

The ILA must be reviewed to determine the agency or agencies having authority over permitting and the applicable ILA development standards for the specific project location. The Port PM can assist with this review.

## Introduction

The Port of Seattle Fire Department is responsible for administrating and ensuring fire and life safety compliance on all Port airport properties and facilities including the proper use of newly installed equipment and maintaining life safety control during necessary system shutdown activities related to construction. To meet this responsibility, the Fire Department requires the assistance of the Contractor to ensure construction projects do not impact the existing life safety systems in place at the airport. For the purposes of this document, all references to “Fire Department,” shall be in reference to the Port of Seattle Fire Department.

The Fire Department performs regular building, construction and fueling inspections to help assure the safety at the airport. These inspections include regular testing of alarms, sprinklers, and other life safety systems. The Fire Prevention division issues permits for system shut-downs, hot work activities, and operational permits. The Port of Seattle Fire Department also reviews construction plans, deferred submittals, and shop drawings for code compliance.

1.2 – Current Codes

The Port of Seattle Fire Department is currently enforcing the 2022 Edition of NFPA 415 - Airport Terminal Buildings, Fueling Ramp Drainage, and Loading Walkways as well as the 2021 Edition of the International Fire Code with Washington State Amendments and as amended by this document.

The Port of Seattle Fire Department requirements are listed in a document titled “Port of Seattle Fire Department’s Code Amendments, Standards, and Interpretations.” All Port of Seattle projects at the airport are required to be designed and constructed in strict adherence to this document:

https://www.portseattle.org/page/design-standards-and-guidelines

5. REGULATED MATERIALS MANAGEMENT

- REGULATED MATERIALS MANAGEMENT

## Asbestos and Other Regulated Materials

The Port of Seattle is committed to preventing exposure of staff, tenants, and the public to asbestos-containing materials (ACM) and other regulated materials including but not limited to lead, PCB caulk/sealant, PCB oils and silica. The Port's Regulated Materials Management (RMM) Program provides comprehensive training, testing, project design, abatement, cleaning, and surveillance to ensure worker safety, maintain ACM at Port facilities in good condition, and support construction projects.

Many terminal building structural members and adjacent building surfaces above suspended ceilings and inside walls are protected by spray-on fireproofing containing asbestos. Subfloors and other components may also have asbestos containing overspray. Before drilling into a floor or wall or removing ceiling systems, the contractor shall request a survey from the Port. Contractors are prohibited from any removal of metal ceiling systems unless approved in advance by Port AV/Maintenance.

Upon discovery of asbestos behind an enclosed space where the color is not blue or wherein there is no asbestos-free signage, the contractor does not proceed with work and calls for a Port inspection before proceeding.

Upon encountering or exposing asbestos-containing material (ACM) not identified in the scope of work, the contractor immediately notifies the Port Inspector and does not further disturb the ACM until and unless given direction by the Port.

Unless specifically identified in contract documents as work by the contractor, asbestos abatement work is typically completed by the PCS RMM Program utilizing a small works abatement contract. Asbestos abatement projects require notification of the Puget Sound Air Pollution Control Agency and Washington State L&I. A waiting period of up to 10 working days after notification may be imposed (depending on the material) before a project can be started. Availability of contract capacity and abatement contractor resources may also dictate the abatement schedule. Early contact with the Port regarding asbestos abatement for a project is recommended so that the required forms can be filed as early as possible, and abatement contractor availability can be confirmed.

All workers involved in construction activities located in areas known to have ACM must attend a 2-hour asbestos awareness training class provided by the Port. Attendance at this class is required before work begins. Contact the Port PM, PCS CPM, CM or Inspector for location and schedule of these classes.

# ENVIRONMENTAL

The City of SeaTac/Port of Seattle Interlocal Agreement (ILA) https://www.portseattle.org/sites/default/files/2020- 12/2018_Interlocal_Agreement_Signed_w_SeaTac.pdf must be reviewed to determine the agency or agencies having authority over permitting and the applicable ILA development standards for the specific project location. The Port PM can assist with this review.

## Introduction

Port AV/ENV provides environmental compliance support for all environmental disciplines including, but not limited to, SEPA/NEPA; water quality and stormwater management; waste management and contaminated soil; construction waste management; air quality; and wetlands and natural resources. Port AV/ENV has environmental strategic objectives that support the Port’s Century Agenda and Aviation Division Strategic Planning Goals. To meet these goals, Port AV/ENV provides support for incorporating sustainable facility design and encourages all contractors to implement environmentally preferable construction practices and recycle construction and demolition debris.

Where references are made to specification sections, Port projects should refer to the project specifications, and tenant projects should refer to the Port’s Tenant Improvement Construction General Requirements.

## National and State Environmental Policy Acts Requirements.

Construction on Port property may not commence until appropriate SEPA and/or NEPA analysis has been completed. Construction on Port property may not commence until AV/ENV has reviewed and approved that project design meets all permits and is in alignment with applicable environmental strategic goals and objectives.

## General Permit Compliance

Where environmental permits have been obtained for projects, contract plans and specifications provide a critical component of environmental permit compliance, and compliance with those plans and specifications is required. Those environmental contract specifications commonly include, but are not limited, to the following:

  - 00 80 00A Attachment A, NPDES Contractor Permit Statement

  - 01 35 43 Environmental Regulatory Requirements

  - 01 57 13 Temporary Erosion and Sediment Control Planning and Execution

  - 01 57 23 Pollution Prevention Planning and Execution

  - 01 59 00 Construction Water Management System

  - 01 74 19 Construction Waste Management

  - 02 41 13 Site Demolition

  - 02 80 00 Facility Remediation

  - 02 82 13 Asbestos Abatement02 61 13 Handling Contaminated Soil

  - 02 83 19 Lead Controls in Construction and Demolition

  - 02 84 16 Light Ballast and Lamp Removal and Management

  - 02 84 33 Removal of PCBs and PCB Containing Material

  - 02 84 33.13 PCB Caulk Removal

  - 31 00 00 Earthwork

  - 32 90 00 Planting

  - 32 92 19 Seeding

  - 32 92 19.16 Hydroseeding for Erosion Control and Landscaping

## Water Quality and Stormwater Management

All construction activities shall comply with applicable environmental permits. The Airport operates under the requirements of a National Pollutant Discharge Elimination System (NPDES) Permit issued by the Washington State Department of Ecology. The NPDES Permit imposes controls that assure that Airport industrial wastewater, industrial stormwater, and construction stormwater discharges meet applicable water quality standards. NPDES controls are implemented by the Airport through the Airport Stormwater Pollution Prevention Plan (SWPPP). Under the terms of the Permit, the Airport is responsible for all industrial and stormwater discharges originating on Airport Property. All construction projects within the permit boundary are subject to the provisions of the permit and will comply with that permit. Any Port or tenant projects outside of the permit boundary must file for a general construction permit, if applicable.

Contract change orders that could affect environmental permit compliance are reviewed and approved by AV/ENV or other designated staff. All applicable environmental permits, temporary erosion and sediment control plans, pollution prevention plans, and stormwater pollution prevention plans for projects to be constructed are maintained and available at the project site or specific location defined by permit.

Construction and demolition activities by Port or tenants shall not interfere with operation of or access to Port stormwater monitoring stations and equipment around the Airport. The party managing construction is responsible for understanding the locations of these stations and equipment that may be impacted by the project.

Specifications Section 01 57 13, Temporary Erosion and Sediment Control Planning and Execution, has been developed to control erosion and sediment transport and air quality related to fugitive dust generated during outdoor construction. If applicable, compliance with all specification conditions is required to assure compliance with the Port’s NPDES permit, unless otherwise approved by Port AV/ENV staff before construction begins.

All temporary erosion and sediment control and pollution prevention measures required for construction work shall be in place before work begins, and those measures shall be inspected daily and maintained as required by contract or as directed by the Port PM. Daily Temporary Erosion and Sediment Control inspection reports shall be kept on site and available for review upon request

All construction stormwater must meet permit requirements prior to discharge. The contractor is required to monitor all construction stormwater discharges. Specific project

requirements are defined in specifications Section 01 57 13 and/or Section 01 59 00. No construction runoff is allowed to drain or be pumped to the industrial waste system without prior approval. Contact Port AV/ENV for Industrial Waste Treatment Plant Discharge Request Form and specific information on how to obtain approval and ITWP policy.

Process water or chlorinated/potable water is not permitted to be discharged to the storm drain system. Process water includes, but is not limited to; wheel wash water, concrete saw cut slurry, road wash water, and sweeper wastewater. Chlorinated and/or potable water must be dechlorinated before discharge.

Where construction stormwater monitoring of a Port or tenant construction site is required, access is coordinated with and granted to Port AV/ENV staff who will conduct that monitoring.

## Contaminated Soil and Groundwater Management

All contaminated site remediation must be performed according to federal, state, and local laws and regulations; contract specifications 02 61 13 Handling Contaminated Soil and others; and/or as directed by the Port AV/ENV.

Before work begins, the contractor provides to AV/ENV a work plan and schedule of work for approval for construction projects where contaminated soil or groundwater is expected to be encountered. Port AV/ENV may need to inspect these projects to assure regulatory or permit compliance, which will be determined no later than the preconstruction meeting.

Port AV/ENV is notified immediately if potentially contaminated soil or groundwater is encountered during construction work.

All construction on groundwater and vapor monitoring wells, including installation, decommissioning, and refurbishing shall be conducted in accordance with WAC 173-160. Plans for these types of construction activities must be approved in advance by Port AV/ENV. Contractors provide copies of Washington Department of Ecology documentation as required by Port AV/ENV.

Using the contaminated soil stockpile facility, operated by the Port, may only occur after approval by Port AV/ENV.

## Hazardous Materials and Waste

Specifications Section 01 57 23, Pollution Prevention Planning and Execution, has been developed to ensure hazardous materials and waste are handled and managed appropriately. Compliance with all conditions of the specification during construction work is required to ensure compliance with the Port’s NPDES permit, unless otherwise approved by Port AV/ENV before construction begins.

Any spill of pollutants that occurs during construction must be reported to Port Inspector and AV/ENV immediately and as required by the applicable Pollution Prevention Plan. Contractors are responsible for immediately reporting to the Port any spill deemed reportable under local, state, or federal statute., in addition to reporting to Port AV/ENV. Spill kits used to contain and clean up any spills of hazardous materials and/or waste must be on site during construction.

Prior coordination with Port AV/ENV is made by the Port PM, PCS CPM, or CM related to hazardous waste removal. Port AV/ENV must be present any time hazardous wastes are

removed from Port property. Port AV/ENV signs all hazardous waste manifests before waste is removed from Airport property.

During project construction, any unanticipated hazardous materials, waste, or contaminated soils encountered during demolition or construction that are not generated by the contractor’s activities shall be immediately brought to the attention of the Port PM, PCS CPM, or CM. The materials shall not be disturbed until proper designation has been determined by Port AV/ENV.

For Port-constructed projects, documentation for universal waste disposal will be submitted to Port AV/ENV no later than 30 days after project completion, but before contract closeout. Abatement of regulated materials must comply with Port abatement requirements identified in contract documents.

## Waste Disposal

Wastewater shall be disposed of according to all applicable federal, state, and local laws or regulations, including but not limited to those of the affected sewer district. All liquid waste discharges must be approved by Port AV/ENV. Wash water of any type, including road washing, is considered process water and not permitted to be discharged to any storm drain system or Industrial Waste System.

Before connecting to the existing industrial waste system, existing storm drain system, or sanitary sewer system, the contractor verifies that the connection to the existing Port system is appropriate, that sufficient capacity and detention is available for the proposed additional loads, and approval has been acquired from the Port. This is documented in the Stormwater Site Plan submittal that is reviewed by the Port.

All hazardous materials and hazardous wastes stored or generated from operations at the Airport are owned by the generator of that waste or material, as the term “generator” is defined in Title 40 of the Code of Federal Regulations or Title 173 of the Washington Administrative Code. This does not include waste generated directly from contractor activities (for example, contractor vehicle maintenance, contractor chemical spills). The contractor must coordinate with Port AV/ENV for disposal requirements.

## Air Quality

Contractors are required to abide by all federal, state, and local air quality/greenhouse gas emission regulations.

Before starting construction and operation of any facilities with point-source emissions (such as exhaust vents, chimneys, and stacks), the contractor must obtain, and retain for inspection if requested by the Port, all necessary regulatory permits including a Notice of Construction Order of Approval from the Puget Sound Clean Air Agency.

Additionally, all contractors regardless of project scope must abide by the following air quality practices:

  - All diesel equipment with an engine of 25hp or greater must be a Tier 4 or higher rated engine. Equipment that does not comply with this standard shall be identified to the Port prior to construction.

  - For non-diesel or low-hp diesel equipment, contractors must use low-emission construction equipment and best available control technology.

  - Equipment must not idle for more than five (5) consecutive minutes unless idling is necessary to serve the purpose of the machine. Stationary emission sources (e.g. portable diesel generators, compressors, etc.) must be turned off when not in use

  - Contractors must have in place appropriate air quality control measures to ensure that construction and public areas are not adversely affected by uncomfortable temperatures, fugitive dust, and other unacceptable air emissions.

  - Burning of any refuse is prohibited

## Construction Waste Management

To support the Port’s strategic goals, contractors are required to develop and implement a Construction Waste Management Plan and final report as defined in specifications Section 01 74 19. The specification provides template forms for both the plan and report. To the maximum extent practicable, contractors working at the Port are encouraged to divert construction waste from the landfill by using salvage, reuse, source-separated, or comingled recycling activities. Quantities are typically reported by weight (tons) unless otherwise approved by the Port. Copies of manifests, weight tickets, recycling and/or disposal receipts or invoices that validate the calculations, or a signed certification of completeness and accuracy of the final quantities reported, are required to be submitted.

## Critical or Sensitive Area Protection

Port properties adjacent to the Airport contain an abundance of critical or sensitive areas, such as streams and wetlands. Disturbance or impact to these areas and their designated buffers is not allowed. Disturbance of critical and sensitive areas and their buffers may only occur in accordance with local, state, and federal regulations or project-specific permits. Port AV/ENV should be contacted to determine whether the project affects or is near these areas.

## Inspections

Port AV/ENV and/or Engineering Construction Management inspects construction sites as needed to assure compliance with applicable environmental regulations and contract specifications.

# AIRPORT OPERATIONS

## Introduction

Port AV/OPS is committed to maintaining the operational continuity of the Airport while upholding the highest levels of safety, security, and customer service. Port AV/OPS comprises several different groups, including construction coordination. For more detailed information on Port AV/OPS requirements refer to specifications Section 01 35 13.13, Operational Safety on Airports during Construction.

Where references are made to specification sections, Port projects should refer to Project specifications, and tenant projects should refer to the Port’s Tenant Improvement Construction General Requirements.

## Coordination of Construction with Airport Operations

Airport operations will continue throughout periods of construction work. Where Airport operations conflict with those of the contractor, the operations of the Airport take precedence. No construction activity will be unreasonably noxious, offensive, or create an unreasonable annoyance or nuisance to others on or adjacent to Airport property.

Port AV/OPS schedules and communicates construction activities with Airport stakeholders. The Port PM, PCS CPM, CM, or Inspector identifies the AV/OPS contact for the project. With support from the Port Inspector, the contractor is solely responsible for scheduling and coordinating its activities with those of the Airport to minimize disruption of Airport operations. Support from Port AV/Maintenance requires a request submission before

8:00 a.m. Thursdays for the following work week to provide escorting to restricted locations.

## Federal Aviation Administration Notice of Proposed Construction or Alteration Requirements

FAA approval is required for certain types of construction at the Airport. All requirements for FAA compliance shall be incorporated into contract documents.

## Noise

Except for the operation of motor vehicles, aircraft, or other transportation equipment, the maximum permissible sound levels at any point shall not exceed those levels established by any state, federal, or local government agency with jurisdiction to regulate noise.

Noise level restrictions are identified in specifications Section 0 50 00, Temporary Facilities and Controls. For work conducted within Airport buildings, noise levels from work activities will not exceed 80 A-weighted decibels.

## Hazardous Wildlife Mitigation and Pest Prevention

Pest prevention requirements:

  - All structural gaps or holes greater than 0.25-inch long or wide are sealed or closed to prevent pest or animal access to buildings and between spaces.

  - Door sweeps on exterior doors are installed for door gaps greater than 0.25 inch to prevent pest access.

  - Unless otherwise agreed with the wildlife biologist, bird deterrents are installed on horizontal exterior structures greater than 12 inches in length and 2 inches in diameter. Deterrents may also be required on interior structures.

## Heat and Glare

Any operations producing intense glare or heat are performed within an enclosed or screened area so that the glare or heat emitted is not perceptible at the lease boundary line of the construction site. Additionally, any glare from activities conducted on the AOA needs to be shielded to assure no interference with the exterior wall deluge system, vision of vehicle operators, flight crews, or air traffic controllers. In addition to screening, bagging infrared detectors is permissible as coordinated with Port FD in advance.

## Equipment Lighting

Cranes and other construction equipment with an overall height in excess of 15 feet must be lowered when not in use and/or during hours of darkness. Equipment stored or operated on the AOA in excess of 15 feet in height must be equipped with obstruction lighting in accordance with FAA regulations or as required by the Port.

## Vehicles in the Air Operations Area

- Markings

Contractor’s vehicles operating within the AOA must display signs of commercial design on both sides of the vehicle identifying the vehicle as the contractor’s. The contractor’s firm or name must appear in letters a minimum of 2 inches high. The company name on the vehicle must match the company name on the driver’s identification badge. See specifications Section 01 35 13.13, Operational Safety on Airports During Construction, for additional details.

## Operations

Drivers of vehicles operating within the AOA must strictly comply with the Port’s Motor Vehicle Operations section of the Airport Schedule of Rules, Regulations, and Charges as identified in specifications Section 01 35 13.13, Operational Safety on Airports During Construction.

During periods of low visibility, the Airport transitions into a restricted access protocol, which only permits essential vehicle traffic on the AOA and precludes contractors or their vendors making deliveries.

## Parking

No parking is guaranteed on the airfield or ramp unless a project has a demarcated and enclosed construction site. On a first come first served basis several parking stalls are located around the facility marked tenant/contractor that have a maximum 2- hour time limit. Airfield project contractors are required to park within their construction site, and not utilize any other airfield or ramp parking. Violators are penalized and run the risk of losing Security Identification Display Area (SIDA) badge privileges.

## Demolition and Construction

- Housekeeping

The contractor is responsible for mitigating any noise, dust, odors, FOD, smoke, obstructions, and other annoyances. To the extent possible, work in public areas should be performed during off-peak periods; in high-volume areas, this may be required. The contractor may not unreasonably encumber the premises with unused materials, equipment, or scaffolds. The terminal buildings must be kept in operation at all times.

Airfield construction contractors are responsible for controlling FOD continually for the project’s duration; this includes mechanical sweeping operations on all construction travel routes on the AOA.

The contractor is responsible for cleaning the work area to the satisfaction of the Port Inspector and AV/OPS. The contractor is also responsible for removing all construction debris and unused products/materials upon project completion. However, debris that constitutes a hazard to Airport operations or creates an unacceptable visual condition must be removed immediately.

## Flagging

When vehicle flagging is required on public highways controlled by the Port or on Airport property, including the bag well and ramp, flaggers are required to submit current certification from the State of Washington (see specifications Section 01 55 26, Traffic Control). Haul routes, if not on the construction documents, are coordinated with the Port at the preconstruction meeting.

## Temporary Construction Barricades

Temporary construction barricades are required for all projects (see specifications Section 01 50 00, Temporary Facilities and Controls, for detailed requirements).

Continual maintenance of construction barricades and partitions in all public areas is required. On the exterior of the project construction barricade or partition, the contractor is responsible for posting 24-hour project contacts in case of an emergency need.

## Protection

Any work in the plenum space above the corridors in the main terminal; Concourses A, B, C, and D; or the north and south satellites requires the area below the work to be barricaded. The barricades are placed so that ceiling tiles or other materials that may become dislodged and fall from shaking or heavy walking, or falling objects from above, do not injure any people below.

## Temporary Ceiling Removal

Before ceiling are removed, Port RMM status must be verified by the Port PM or Inspector. Some areas of the terminal contain asbestos fireproofing above the metal and acoustical tile ceilings. Metal ceiling tiles may not be removed by a contractor unless approved in advance, Port PM or Inspector to confirm and coordinate when metal ceilings require removal by Port AV/Maintenance or PCS. Any open ceilings shall be covered with white fire-retardant plastic sheeting, at least 6 millimeters thick,

between shifts (see specifications Section 01 50 00, Temporary Facilities and Controls for detailed requirements).

## Equipment in the Terminal

Storage of personnel- or scissor-lifts inside the terminal in locations outside barricaded work areas is permitted only with approval from AV/OPS and AV/Maintenance. During nonworking periods, all equipment of this type should have a placard attached that includes the owner or renter name, project name, project number and a 24-hour point of contact should the lift need to be relocated during off-shift hours or weekends.

Power to charge equipment may not always be available in storage locations provided to contractors. Coordinate charging with Port Inspector to avoid overloading circuits.

Equipment, including ladders and job boxes, used on site shall have a sign identifying the name of the contractor, 24-hour contact information, and the project.

## Direct Digital Control System

The HVAC building automation control system (Siemens DDC) has experienced significant impacts due to damage during demolition. The contractor contracts with Siemens Building Technologies Division before any demolition by any trade of ceilings and walls. Siemens will note work area on DDC graphics, secure Field Level Network (FLN) wires to mechanical equipment and remove temperature sensors. Contractor does not cut any DDC wiring.

## Utility Shutdown Impacts

The contractor should be prepared to provide temporary services to tenants or the Airport should they affect such basic services as HVAC, water, electric, or plumbing. This may be during a simple utility shutdown or a long-term period when modifying HVAC for instance.

## Laydown Areas and Office Operations

No office areas are set up anywhere in the Airport facilities without prior Port approval. Contractors and their subcontractors store materials and equipment within areas identified in the project plans or as identified by the Port at the start of the project. Mechanical and electrical rooms are not acceptable locations for storage or contractor field offices.

## Stored Materials

  - Any and all materials and equipment used for construction generally needs to be stored within the project boundaries. Additional laydown and storage space may be available through the Port PM or Construction Manager per specifications Section 01 50 00 (c), Project Logistics Appendix. Airport activities outside the project area shall not be affected and must be kept operational.

  - All construction materials allowed to be stored in areas accessible to the general public must be protected by full height (approximately 8 feet) barricades acceptable to the Port (see specifications Section 01 50 00, Temporary Facilities and Controls). If stored in areas other than a tenant's leased area, the tenant must coordinate such storage with the Port.

  - Stored materials, inside and outside the project boundary, must be labeled with contractor name, 24-hour point of contact information, project name and project number

  - See Section 4, Fire Department, Paragraph K, Construction Storage, for further details on storage requirements.

Tenant Improvement Design and Construction Process Manual, Section 3.C.7, contains information on availability of tenant contractor employee parking and tenant contractor logistics space for tenant projects. Generally, space is not available within the terminal building. Limited space may be available for rent.

## Site Access, Deliveries, and Removal of Demolished Materials

See Paragraph L for work hours and time restrictions around use and occupancy of the Airport terminal building.

## Deliveries and Removals

Deliveries or removals via the arrivals or departures curbs are only considered when coordinated in advance. Required information includes company operating vehicle; vehicle type/size/color; vehicle license plate; driver name and cell number; and expected arrival and departure time. Driver is required to stay with the vehicle entire time.

Personnel access and material deliveries to the worksite are to be by designated routes only. Pallet jacks or hand carts being used inside the terminal to move materials must have non-marking wheels or casters. Pneumatic wheels are required when transporting material across the central terminal granite floor. Specific route and weight across the central terminal granite floor must be approved. In certain circumstances, laying down plywood or Masonite on the path of travel may be required to avoid damaging the terrazzo and granite flooring inside the terminal. All routes must be delineated and left clean.

In general, tenants and their contractors are not permitted to enter restricted Airport areas, except where no other access route to the premises is available. However, should an item be of such size or configuration that prevents it from being physically transported along the designated route, permission to enter the restricted area, under supervision and after stipulated protective measures have been taken, may be granted by an authorized Port representative.

Limited use of loading dock facilities and freight elevators is granted to the contractors by reservation. Outside regular working hours, such facilities may be made available by reservation and at the tenant's cost. Materials and tools moved through the load dock will be inspected. Inspection staff are available for limited hours. After hours deliveries may incur additional costs.

The contractor shall not use baggage carts provided by the Airport’s baggage cart vendor to transport or store equipment or construction materials.

Oversized materials that do not fit in any of the available elevators may be eligible to be transferred from the nonsterile area into the sterile area depending on sufficient advance notice and subsequent Transportation Security Administration (TSA) and

Airport Security permission. Minimum review and approval process is typically 2 weeks. This movement is known as a “reverse push” and is typically routed via one of the concourse passenger exit lanes. This option is not available at Concourse B and may become unavailable at all concourses as specialized doors are installed in the exit lanes.

## Elevators and Hoistways

The contractor may use designated freight elevators and shall not use passenger elevators for transporting materials to and from the worksite. The contractor may schedule material hoisting time slots with the Port Inspector in advance. The tenant coordinates its move-in schedule of furnishings, accessories, and fixtures with the Port Inspector. Any damage to elevator cabs is repaired by the Port and charged to the tenant at costs plus overhead. Loads will be centered and not exceed the nameplate capacity.

Public passenger-only elevators are not available for contractor use. Public elevators are not intended to move construction materials unless permission is provided by the CSR. Costs, plus overhead, for the temporary threshold bridge installation and removal are charged to the tenant. Airport service and passenger elevators have a 500-pound threshold crossing limit for wheels. All interior finishes are protected, and the cab immediately cleaned of any dust or debris.

## Use of Lobbies and Concourses

No concrete, plaster, terrazzo, debris, or other bulk materials may be brought through lobbies or concourses used by passengers unless written permission is obtained from Port AV/OPS. All existing work must be protected against damage during the contractor's work.

## Construction Dumpsters

A dumpster may be placed on Airport drives but only during very limited hours and for limited durations.

Placing a dumpster on the ramp level for use in support of an interior terminal project is unlikely and only approved under special circumstances other than inside tenants leased space when the dumpster is on behalf of that tenant’s ongoing project. The contractor should be prepared to store demolition materials during the shift in which demolition occurs and remove them at the end of the shift.

Construction waste management must be included in Construction Waste Management Plan as specified in specifications Section 01 74 19, Construction Waste Management.

Food waste and other organic matter that may become a wildlife or pest attractant shall not be placed in construction dumpsters. Lids must be secured when dumper is not in use to limit access of animals to contents.

## Work Hours, Holidays, Black-out Periods, and Other Time Restrictions

- Standard Construction Work Hours

Unless otherwise arranged with the Port, construction hours are as follows:

Standard day shift work hours: 0700 – 1530 (7:00 a.m. until 3:30 p.m.), Monday through Friday. The contractor limits activities so there is no disruption to Airport operations.

Standard night shift work hours: 2030 – 0500 (8:30 p.m. until 5:00 a.m.), Sunday through Friday. All work considered disruptive to Airport operations is performed during periods of low airport activity (see project specifications for specific project requirements). Disruptive work includes but is not limited to:

  - Work within tenant offices

  - Conduit routes over and around the baggage systems

  - Equipment and furniture moves and deliveries

  - Work that creates noise, dust, or odors

Work outside standard work shift hours, as defined in this section, can be requested and may be granted by the Port Inspector, CM, or PM. No work outside standard work hours, as defined in this section, is allowed without written approval from the Port.

## Port Staff Holidays

  - January – New Year’s Day

  - January – Martin Luther King Jr. Day

  - February – Presidents Day

  - May – Memorial Day

  - June – Juneteenth

  - July – Independence Day

  - September – Labor Day

  - November –Thanksgiving Day and day after

  - December – Christmas Day and either day before or day after

## Construction Blackout Periods

During seasonally high travel volumes, terminal operations may result in contractors and suppliers being subjected to restrictions by the Port regarding hours of work, scheduling, and coordination of work.

## Other Specific Time Restrictions

  - Floor core drilling should occur between the hours of 2400-0400 (12:00 a.m. to 4:00 a.m.) unless approved otherwise by AV/OPS.

  - The central load dock is permitted for use to access freight elevator 3F but only between the hours of 1400 – 0400 (2:00 p.m. and 4:00 a.m.

# TRAFFIC AND LANDSIDE OPERATIONS

## Introduction

Port AV/OPS/Landside is responsible for maintaining safe and effective vehicular and pedestrian access to the Airport. To meet this responsibility, Landside requires the assistance of the contractor to ensure construction projects do not impact Landside operations and facilities.

Where references are made to specification sections, Port projects should refer to the project specifications, and tenant projects should refer to the Port’s Tenant Improvement Construction General Requirements.

Contractors are required to abide by specifications Section 01 55 26, Traffic Control.

## General

Landside is responsible for maintaining operations in a variety of Landside facilities, including the following:

  - Northern Airport Expressway, between State Route 518 and the main terminal roadway system (including the ramps at South 170th Street and Air Cargo Road)

  - Air Cargo Road, between South 154th Street and the City of SeaTac right-of-way located just north of South 188th Street (including the Service Tunnel)

  - South 160th Street, between Air Cargo Road and the City of SeaTac right-of-way located at Host Road

  - South 161st Street, between Air Cargo Road and the AOA gate

  - South 170th Street, between Air Cargo Road and the City of SeaTac right-of-way located at the Northern Airport Expressway ramps

  - Main terminal roadway system, including the Departures/Upper Drive, Arrivals/Lower Drive, and all associated recirculation ramps (including the South 182nd Street access at International Boulevard/State Route 99)

  - Main terminal parking garage, including the third-floor ground transportation center entrance and exit, fourth floor entrance, north and south parking entrances, and the North Toll Plaza

  - North and south employee parking lots

  - South 160th Street ground transportation and taxi holding lots

  - Doug Fox public parking facility

  - Bus maintenance facility and transportation operations center

  - Cell phone lot waiting area

## Project Definition

Before starting construction, the contractor and Port PM, PCS CPM, CM, or Inspector evaluate the project’s anticipated scope and schedule to identify if, where, when, and how severely

the project will affect vehicular and pedestrian traffic operation and safety. Typical questions to be considered include the following:

  - Which Landside facilities will be affected by the project?

  - Will the project require closing any of these facilities on temporarily or permanently? Will the closures involve a partial or full closure? Will the closure affect the curb, shoulder, or sidewalk areas? Will the closure affect employee or public parking facilities?

  - How long will these impacts last? During what hours of the day will they occur? During what months of the year will they occur?

  - Will existing Landside operations be affected? Will employee or rental car bus systems be affected? Will ground transportation services be affected (including public transit, scheduled services, unscheduled services, taxis, and limousines)?

  - How much and what type of construction-orientated traffic will be generated? What routes and access points will be used?

  - Will any project material (for example, pipes, beams) or construction equipment (for example, cranes) deliveries affect any of the Landside facilities?

Any project that requires the partial or complete closure of any Airport roadway (including travel lanes and shoulders) requires a traffic control plan. The contractor coordinates with the Port Inspector and AV/OPS CSR to determine the level of coordination necessary, scope of traffic control plans to be prepared as part of the project, and scope of the traffic operations analysis if necessary. The contractor also considers the following:

  - Identify potential constraints likely to be applied to the project as a result of Landside operations (for example, closure of part of the Arrivals/Lower Drive will not be allowed between 1000 - 2400 (10:00 a.m. and 12:00 a.m.)).

  - Provide further direction on the scope of the traffic control plans to be included in the design documents.

  - Provide detailed direction on the scope of laydown areas adjacent to or within Landside facilities.

  - Identify any other potential impacts on Landside facilities due to the project (for example, extension of the water line will require temporary shutdown of employee bus driver break room).

  - Review the results of the traffic operations analysis, if necessary.

  - Identify special considerations to be included in the project specifications.

If a traffic control plan is deemed necessary for a project, as described by the project contract documents, submittal and approval are required before construction begins.

# SECURITY

## Introduction

Where references are made to specification sections, Port projects should refer to the project specifications, and tenant projects should refer to the Port’s Tenant Improvement Construction General Requirements.

All contractors working at the Airport are subject to current Department of Homeland Security / Transportation Security Administration (DHS / TSA) regulations as detailed in specifications Section 01 14 13, Airport Personnel Identification Access Control. These requirements identify how to get badges for access into and through Airport facilities and maintain compliant and secure project construction practices.

The Port Credential Center is responsible for issuing identification badges and keys for restricted and public areas and assigning access into restricted areas. Airport Security is responsible for ensuring contractors conduct operations so that all security requirements and practices identified in the Airport Security Plan are maintained.

## Identification and Facility Access

- Badges

  - In all areas of the Airport, the contractor’s personnel must obtain and wear above the waist on their outer garments photo identification (ID) badges issued by the Port Credential Center. More information on the ID badge program can be found at this link: https://www.portseattle.org/employee-services/credentials-trainings

  - Access for specific doors must be requested and approved after the badge is obtained. Some locations may not be accessed without an escort

  - All badge holders must submit to employee screening

  - At the end of the contract, the contractor is charged for each badge not returned. The cost for unreturned badges is found at the above link

## Keys

  - The contractor submits a key request at the Port Credential Center requesting keys. The key request will be submitted a minimum of 2 weeks before construction begins.

  - A deposit for each security key is required before the requested key is issued. All costs for obtaining security keys are identified at the above link and are at the contractor’s expense.

  - After all keys are returned to the Port Credential Center, the deposit is returned. The deposit is forfeited if the key is lost or not returned.

## Cores

  - Temporary construction cores are requested through the Port Inspector or Project Manager. The Port makes a capital support request to the Port Lock Shop. Support requests are due Thursday before 08:00 for the following week.

  - At the completion of the project a project support request is required to remove the temporary cores and install the final cores.

## Terminal Work

When coordinating construction barricades, any special situation that may affect the security of the Airport is identified and discussed with Airport Security. See specifications Section, 01 50 00 Temporary Facilities and Controls, for more details on construction barricades.

## Perimeter Fencing

Before removing or making holes in the Airport perimeter fencing, the tenant/contractor obtains permission and approval from Airport Security and takes adequate precautions to prevent entry by unauthorized personnel or animals. Any modifications to the perimeter fence are communicated to AV/OPS/Wildlife to allow for appropriate actions to prevent hazardous wildlife from entering the airfield.

Any modification and/or relocation of the AOA perimeter fence line (whether temporary or permanent) must be submitted by Airport Security to the TSA for approval and inclusion into the Airport Security Plan. A minimum of 45 calendar days is required for the approval process. Gates must be either staffed or locked at all times. The AOA perimeter fence line must be clear and free of all debris, storage of materials and equipment, vehicles, or aboveground facilities for a distance of at least 5 feet on both sides of the fence.

## Restricted Areas

When work is to be performed within designated Airport restricted areas, contractors may access only those areas of work or storage designated by the Port Inspector, Construction Manager, PM, Airport Security, and authorized by the Port Credential Center. Restricted access points must be either staffed by a Port construction support specialist or locked at all times. All prohibited items must be locked up and secured when left unattended.

All field access via the perimeter fence is to be reviewed in advance by the Aviation Security. Any modifications to access gates or the perimeter fence is strictly prohibited without written approval for Aviation Security. Vehicle gate access will be reviewed utilizing staffed gates whenever possible.

After construction is completed, all exterior doors and gates leading to a restricted area must have the appropriate security signs and must be incorporated into the Airport’s security system. (Signs are typically supplied by the Port. Airport Security should be contacted for details on appropriate signs. Security devices are provided and installed by the tenant. Coordinate terminations and programming with the Port during design to clearly indicate roles and responsibilities.)

All construction documents for new construction and/or modification of facilities or fencing leading to the AOA and/or restricted areas shall include raceways, wiring, devices and hardware, and all equipment and device installation required for incorporation into the Airport Security access control system.

# CONSTRUCTION MANAGEMENT

## Introduction

Construction management ensures projects are executed using industry best standards for construction processes and procedures within the project’s contract terms. Port Construction Managers and Inspectors provide a key role in supporting the contractor in coordinating and facilitating work at the Airport while complying with the Port’s rules, standards, and guidelines.

Where references are made to specification sections, Port projects should refer to the project specifications, and tenant projects should refer to the Port’s Tenant Improvement Construction General Requirements.

For tenant projects, please refer to the Tenant Improvement Design and Construction Process Manual for information about construction processes such as construction submittals, deferred submittals, substitutions, requests for information, construction barricades, punch lists, and other tenant-specific items.

## Notice to Proceed and Pre-Construction Meetings

No construction work begins at the Airport without receiving Notice to Proceed and participating in a preconstruction meeting. For tenant projects, see Tenant Improvement Design and Construction Process Manual, Section 5, Pre-Construction, for detailed requirements.

## Schedule Management and Coordination

Before work begins, the contractor submits a detailed progress schedule for approval. For tenant projects, see the Tenant Improvement Design and Construction Process Manual, Section 5, Pre-Construction, for detailed requirements.

Weekly look-ahead schedules are used to identify and communicate project activities to a wide variety of Port stakeholders. This supports the contractor in understanding what necessary steps are required to begin and execute work.

Weekly coordination meetings with Port personnel and contractors are required, unless otherwise agreed with the Port CM, Inspector, PCS CPM, or PM.

## Construction Coordination

The Airport is an operating facility that must remain in full operation throughout the term of this contract. Where facility operations conflict with those of the contractor, the facility operations take precedence over those of the contractor. The contractor is solely responsible for scheduling and coordinating its activities with those of the facility to assure minimum disruption of facility operations. See specifications Section 01 31 13 Project Coordination.

## Construction Advisory Form

Communication with Port AV/OPS is critical to Airport safety and project progress. A minimum of 2 weeks’ advisory notice must be given to the Port Inspector  before any project begins and before any work that will

impact Airport operations. The contractor is responsible for coordinating exact dates and times of all activities regarding access for crew, material, and equipment delivery.

## Coordination Meetings

The Port conducts regular construction meetings to coordinate the work of the contractors, answer questions, and resolve issues. The Port then publishes minutes from these meetings.

## Coordination with other Port Work

During construction, work by others may be occurring within or adjacent to the boundaries of this project. If so, the contractor will cooperate with the Port and other contractors to prevent impact to any other construction projects.

## Pre-installation Meetings

Based on project scope, contractors schedule pre-installation meetings to coordinate work. The purpose of these meetings is to review scope of work, identify participants, and plan activities that involve the Port or other contractors and could impact Port operations. The contractor works with the Port CM, PM, PCS CPM, or Inspector to determine what work requires pre-installation meetings.

Pre-installation meetings are scheduled by the contractor and held at least five working days before any work is started by the contractor or any subcontractor. The Port CM or Inspector may waive this requirement if deemed unnecessary or request additional meetings as required.

## Contractor Quality Control Program

The contractor provides a quality construction product. To establish the level of quality, the contractor meets the Port design and quality standards of the existing base building as identified in project documents. This level of quality includes, without limitation, the material grades, thickness, and strengths; any national or international standards that must be met; any samples that must be submitted; any testing required to assure quality; installer experience required; all fabrication and installation tolerances; and other related quality items.

The Port has the right to inspect all work at any time to assure that the contractor provides the minimum quality level required.

## Utility Shutdown Coordination: Heating, Ventilation, Air Conditioning, Plumbing, and Electrical Utility Systems

All construction activities interfacing with existing systems must be fully coordinated with Port AV/Maintenance to preserve system integrity. Extensive coordination is required to facilitate system and utility shutdowns for construction activities. All shutdowns require complete and extensive planning to ensure the operations of the Airport continue with minimal impacts.

The contractor coordinates the work with the Port Inspector and AV/Maintenance. A request for shutdown of a utility at the Airport is accepted only from the contractor or authorized tenant’s representative.

To manage the risk associated with shutdowns and minimize the time a system is down, an Airport Systems and Utility Shutdown Request (SDR) must be submitted and approved well in advance of the work. The contractor coordinates the work with the Inspector and AV/Maintenance. The SDR must be completed (all necessary sign-offs received and SDR distributed) a minimum of 10 working days plus 72 hours before the shutdown date.

Weekend days and holidays do not count as part of the 10 days or 72 hours.

  - 10 days plus 96 hours’ notice is required for domestic water system shutdowns.

  - SDRs that have an impact to Airport operations or tenants may require the submission of a Construction Advisory Form along with the SDR, as required by AV/OPS. This form must be completed 2 weeks before work begins.

The contractor does not turn on or off any utility on the Airport premises. Port AV/Maintenance performs all shutdowns and restarts existing systems. In some cases, if coordinated and agreed to in writing, the contractor may perform a shutdown.

All building interior preparation will be completed before scheduled shutdown time (for example, restrooms closed, signs put in place advising public of no restroom facilities). Port AV/Maintenance does not turn off or on any utilities without the contractor present. The contractor advises the Inspector when the work is finished so that Port AV/Maintenance personnel can be called to place the utility back in service. If the utility service is shut down within the contractor’s requested time frame and the contractor does not perform the work as scheduled, the contractor or tenant is responsible for all Port costs associated with the utility shutdown.

Fire system shutdowns are coordinated through the Port Inspector and carried out according to the guidelines outlined in the project specifications. See Section 4 Fire Department. The contractor also submits a plan for the Port Inspector’s approval detailing the contractor’s actions regarding accidental damage to a fire detection or fire suppression system.

See specifications Section 01 31 13, Project Coordination, for more details.

## Construction Inspections

Port stakeholders and consultants may observe or test the contractor's work to determine compliance with approved project documents. The Port monitors construction processes and methods to ensure compliance with Port and industry standards and evaluates whether material, equipment, furnishings, fixtures, systems, and finishes installed satisfy the requirements of the "approved" or “approved as noted” construction documents, shop drawings, product data and sample submittals, and the contractor's warranties.

The contractor permits and provides inspectors access to all work areas and to off-site facilities used to store or manufacture materials, furnishings, fixtures, and equipment to be incorporated into the work. The contractor responds to any other reasonable request that furthers the inspector’s ability to observe or complete any tests. Such inspections and tests do not relieve the contractor of any obligations under its owner-contractor agreement.

## Inspections

During construction, various Port stakeholders have a role in inspecting projects as identified in the Table 1.

Table 1. Stakeholder Inspection Roles

| Stakeholder | Inspection Role |  |
| --- | --- | --- |
| Port Inspector | Oversees project for compliance to: - Plans - Specifications - Port standards including maintainability standards |  |
| Port Construction Safety | - Construction safety |  |
| ABD | - Applicable codes - Deferred submittals - Building - Plumbing - Mechanical | - Demolition - Commissioning - Temporary C of O - Final C of O |
| Port FD | - Deferred submittals - Temp barricades - Fire sprinkler systems - Alarm and strobes | - Hot work permits - Temporary C of O - Final C of O |
| AV/Maintenance and AV/F&I | - Equipment accessibility - Discipline conflicts - Potable water connection and testing - Temporary power connection - Waterproofing applications | - Inspections before covering ceilings and walls. - Building envelope (for example, roofing, exterior window wall systems, roof top equipment, ceiling systems) |
| State of Washington L&I | - Electrical - Vertical conveyance | - Temporary C of O - Final C of O |
|  | - Health Department - Liquor Board | - Airport Dining and Retail Manager |
| Other Inspections |  |  |

The ABD requires evidence of these inspections to issue a C of O. In addition to the above inspections, intermittent inspections by Port AV/Maintenance or AV/F&I may occur to verify that architectural, structural, mechanical, electrical, plumbing, HVAC, and communication systems are installed per Port standards.

Port AV/ENV will conduct periodic inspections to verify compliance with applicable stormwater, other water resources permits, waste management, and any other environmental regulations associated with the project.

Port AV/OPS/Wildlife will conduct periodic inspections to verify compliance with Port rules and regulations.

## Inspections Coordination

Construction Inspections

In general, the contractor is responsible for scheduling required ABD, Port FD, Engineering, and AV/ENV inspections and for ensuring that inspections are

completed. The Port may conduct any inspections it deems necessary and will bring any irregularities to the tenant or contractor’s attention. The Port has no liability for failing to make any such inspections, or for failing to bring such irregularities to the tenant or contractor’s attention.

The tenant or contractor notifies the Port Inspector 48 hours before covering up work so that the work may be reviewed by appropriate Port AV/F&I, AV/Maintenance, and other Port stakeholder representatives. Any work covered up without first providing 48-hour advance notice may be removed.

The contractor provides for the Port and any party designated by the Port all access including ladders, access doors, lifts including operator, and ventilation needed to review the quality of the work.

Special Inspections

Required IBC special inspections are accomplished by inspection firms or certified inspectors approved by the ABD. The Port Inspector and ABD Inspector will take part in, and must be notified before, those special inspections required by IBC. Copies of all inspection reports and tests are forwarded to the Port Inspector and ABD.

The ABD’s final acceptance of occupancy is when the ABD has received all inspection reports, certifications, and record documents. The ABD’s inspection file must be complete and satisfactory before a C of O is issued.

Defective Work

Port Inspectors are authorized to reject any work, fixtures, systems, materials, equipment, furnishings, or any work component that does not conform to the approved construction contract documents.

Port Inspectors conduct reviews against approved construction contract documents, shop drawings, and samples to determine whether the work is acceptable. If the appearance and/or performance of any work element fail to conform to the plans, specifications, codes, and standards, a nonconformance report will be submitted by the Port in writing to the tenant and the contractor.

Removal or modification, as directed by the Port Inspector, ABD, or Washington State L&I inspector, of any work that does not conform with the approved construction documents, codes, Port standards, or RAC, is at the contractor’s expense. Failure to take immediate action to remedy the situation may result in suspension of the building permit.

## Electrical Room Access for Work or Work Requiring Electrical Shutdowns and/or Project Electrical Safety Meeting

Requests for Port AV/Maintenance Electrical Department escorts and room access must be submitted by 8 a.m. Thursday for the following week and are required for access to power centers, chiller distribution room, emergency, and STS power rooms. Work in these rooms requires a Capital Improvement and Expense Project Support Request completed by the Port.

Projects that require electrical room access must hold a pre-installation or project electrical safety meeting with the electrical shop before proceeding.

When a contractor requires access to the other electrical rooms, they are to arrange through the Port of Seattle Construction Inspector assigned to the project.

The Port AV/Maintenance Electrical Department will determine whether a Port electrician will be present during access to the electrical room(s) provided an advance notice support request has been submitted.

## Temporary Utility Connections

Specifications Section 01 50 00, Temporary Facilities and Controls, provides more details about temporary utility connections.

Temporary connections are used during construction and then completely disconnected and removed:

  - Electrical—An application for connection for temporary electrical power shall be submitted for approval to Port AV/F&I.

  - Water—An application for connection for temporary water services shall be submitted for approval to Port AV/F&I. Each temporary water connection requires a certified backflow prevention device (RPBA) that was tested by a certified tester (report reviewed by Port AV/Maintenance and AV/F&I) preferred or by Port AV/Maintenance prior to use. This includes all hoses and any other type of temporary connections.

## Project Close-Out

Where references are made to specification sections, Port projects should refer to the Project specifications, and Tenant projects should refer to the Port’s Tenant Improvement Construction General Requirements.

For Tenant projects, see the Tenant Improvement Design and Construction Manual Section 7, Completion and Close-out, for detailed close-out requirements:

No project is a successful project without completing all the work associated with the construction contract, including but not limited to the following:

- Complete stabilization of any disturbed areas

- Request, conduct, and complete punch list inspections and corrections

- Complete commissioning

- Construction Waste Management Final Report per specifications Section 01 74 19 (b)

- Prepare and submit operations and maintenance manuals

  - Fully text searchable PDF format and table of contents

  - warranties, and dates for warranties.

  - Contractor must designate a contact for responding to warranty claims post project completion.

- Microsoft Excel Computerized Maintenance Management System (CMMS) spreadsheet for Port-maintained equipment

- Submit as-built redlines

- Complete training

- Complete Certificate of Occupancy

- Prepare as-built CAD drawings with fully text searchable PDF formats. As-builts will include panel schedules in Port standard electronic Excel format for all new panels and for all panels where circuits have been modified. Mechanical AutoCad file with architectural background and XREF files to be sent to Siemens Building Technologies Division for DDC graphics

- Return badges and keys

- See specifications Sections 01 74 00 Cleaning, 01 78 23.13 Aviation Operations and Maintenance Data, 01 78 29 As-built Redline Documents, 01 91 00 Commissioning, 01 79 00 Training, 01 77 00 Project Close-out for more detailed information

# APPENDIX A — DEFINITIONS

Whenever in this document, the following words and defined terms are used, the meaning will be as follows, which meaning will be applicable to both the singular and plural forms thereof:

| Word | Definition |
| --- | --- |
| Airport | The entirety of Seattle-Tacoma International Airport (Airport) and properties owned by the Port of Seattle in and around the Airport as shown on the Airport Layout Plan |
| Airport Building Department (ABD) | The authority having jurisdiction over building permits and acceptance. |
| Airport Building Inspector | The ABD representative responsible for the building permit processing for Airport projects and for the code inspection of construction projects at the Airport |
| Aviation Division | The division of the Port of Seattle that has authority and control of the Airport |
| International Building Code (IBC) | Building code used by the Airport |
| City | City of SeaTac or City of Des Moines as applicable. |
| concessionaire | Any person, firm, corporation, governmental agency, or other entity which has entered into a contractual relationship with the Port of Seattle for lease, or rental, or occupancy of a space inside a facility on Port property. |
| Construction Manager (CM) | The authorized representative of the Engineer that is generally located on or near the Project Site and assigned to be the primary point of contact for the Contractor. The Construction Manager has immediate, day-to-day charge of the on-site administration of the Project. The Construction Manager will be identified by the Port, in writing, subsequent to Contract Execution Date. This may include Sr. Construction Manager and Principal Construction Manager |
| contract document(s) | Document(s) that governs the construction relationship between the Port of Seattle and contractor or tenant and contractor working on Port property. |
| contractor | Individual, partnership, firm, corporation, joint venture, or other business entity with whom the Port of Seattle, or its tenant, has entered into a contract and who is referred to in contract documents as the contractor; contractor means and includes the contractor and all of its representatives, subcontractors, and suppliers. |
| County | King County |
| day | A calendar day unless otherwise specifically designated |
| drawing(s) | Graphic presentation of the work, or parts thereof, that indicates the size, form, location, and arrangement of the various work elements |
| Engineer | Chief executive officer of the Port of Seattle's Engineering Services Department (the Director, Engineering Services) and such agents, including the Construction Program Leader and Construction Manager, as are authorized to act in his/her behalf. |

| Engineering Department | The Port of Seattle Engineering Department comprising Design, Construction Management, and Construction Safety |
| --- | --- |
| Final Inspection | The final inspection is the inspection that occurs to verify the contractor’s punch list items and items added by the Port Inspector from punch list inspection are complete. |
| Fire Chief | The head or head’s authorized representative of the Port FD. |
| Fire Department (FD) | The Port FD located at the Airport |
| Improvements | All buildings, structures, and facilities, including paving, fencing, signs, and landscaping, that are constructed, installed, or placed on, under, or above any Airport building site by or on behalf of an Airport tenant or the Port |
| Notice to Proceed | Notice to Proceed is formal notification issued by the Port of Seattle, indicating the contractor can begin physical work at the project site. |
| Port (Owner) | The Port of Seattle, its commission, employees, and other authorized representatives with delegated Port authority regarding the work. |
| Port Construction General Requirements | General requirements for working at the Port typically presented as Division 1 Specifications on Capital Projects and attached to design and construction documents for tenant Improvement projects. |
| Port Inspector (Inspector) | The Engineer’s authorized representative assigned to monitor all construction work on Port property, including ensuring contractors comply with Port rules and regulations; support coordination efforts related to performing work at the Port and performing inspections of the contractor’s work including compliance with plans and specifications as well as installation. |
| Project Manager (PM) or Capital Project Manager (CPM) | The Port of Seattle’s authorized representative assigned to lead and coordinate all aspects of project development and implementation |
| punch list inspection | Punch list inspection is the activity that occurs prior to final inspection. The contractor prepares a punch list before requesting a punch list inspection by the Port Construction Inspector. Punch list items are limited to administrative requirements of the contract (for example, final project record documents), training, landscaping, and minor deficiencies in the work requiring correction; a punch list inspection is not be requested or granted if the work is incomplete |
| SEPA | State Environmental Policy Act (RCW 43.21C) and implementing regulations (WAC 197-11) |
| site or building site | Airport land or building area identified in Port contract documents (that is, plans, specifications, or lease agreements) upon which improvements are to be constructed |

| specifications | Portion of the contract documents consisting of the written requirements for contract administration, materials, equipment, systems, standards, and workmanship for the work and performance of related services |
| --- | --- |
| PCS Construction Project Manager | The authorized representative of Port Construction Services that is to be the primary point of contact for the PCS project. The Construction Project Manager has responsibilities, as needed, to guide projects through design, permitting, contracting, construction, and inspections to achieve final completion in full compliance with Port, building department, and tenant requirements. The PCS Construction Project Manager will plan, schedule, assign and direct the work of PCS crews and contractors as agreed upon in the PCS Work Request. |
| Port Standards | Level of products and installation, quality, achievement identified by discipline that is considered acceptable or desirable by Port AV/F&I |
| State | State of Washington |
| subcontractor | Business entity that has a direct contract with the contractor to perform a portion of the work; subcontractor means and includes the subcontractor and its authorized representatives |
| sub-subcontractor | Business entity that has a direct or indirect contract with a subcontractor to perform a portion of the work. |
| supplier | Vendor, supplier, distributor, or material provider that supplies material or equipment used in the performance of the contract. |
| tenant | Any person, firm, corporation, governmental agency, or other entity that has entered into a contractual relationship with the Port for lease, or rental, or occupancy of a building, land, or other facilities on Port property |
| tenant improvement | Any improvement project performed by a person, firm, corporation, governmental agency, or other entity which has entered into a contractual relationship with the Port for lease, or rental, or occupancy of a building, land, or other facilities on Port property |
| wildlife/pest | The Wildlife Hazard Management and Conservation Program organized under Airport Operations to implement FAA 14 CFR 139.337 under the Airport Wildlife Hazard Management Plan; Unified Pest Management Program is one component of the wildlife management program at the Airport |
| Work | Work means the completed construction as a result of the furnishing of all labor, materials, equipment, and all incidentals necessary for successful construction completion; work is sometimes generally referred to as the "project" |

# APPENDIX B — DAILY PRE-HOT WORK CHECK LIST

### Port of Seattle Fire Department Daily Pre-Hot Work Checklist

Date:

Time:

Location/Space Hot Work:

Company Name: 		Name Performing Checklist:

Check all that Applies: Hot work operator shall not fill out Pre-Hot Work Checklist.

Y N/A

### Required Precautions

Extinguishers are operable and fully charged. 2-A: 20-B:C min. size

Hot Work equipment in good working condition

### Requirements 35’ from Hot Work

Y  N/A	*To determine fire watch requirements

*Floors swept clean, remove or shield combustibles using approved welding fire blankets or curtains.

*Isolate or remove potential sources of flammable gas, ignitable liquid, or combustible dust/lint.

Shut down ventilation and conveying systems (Contact Port Inspector).

*Remove combustibles and consider second fire watch on opposite side of floor, wall, ceiling, or roof when openings exist, or thermally conductive materials pass through.

### Hot Work on/in Closed Equipment, Ductwork and Piping

Y  N/A

Y  N/A

Contact Fire Prevention prior to all hot work performed on/in closed equipment, ductwork, and piping.

### Hot Work on Ramp

No hot work within 50 feet aircraft, all hot work must cease when aircraft is fueling within 100 feet.

All Hot works visible from or on ramp needs appropriate shielding (fire blankets or fire umbrellas) to prevent UVIR activation. If not possible, contact Fire Prevention Division to identify UVIR’S to cover (206) 787-5327

Daily Pre-Hot Work Checklist - Continued

Elevated Hot Work Areas

Y N/A

All elevated hot works producing sparks/slag shall require a designated fire watch and shall be maintained during all breaks.

Elevated hot works requires inspection of space below.

If sparks/slag fall, space below shall be cordoned off to protect other workers.

### Fire Watch/Fire Monitoring the Hot Work Area

Y N/A

Perform a continuous fire watch during hot works and breaks.

*30-minute post hot work fire watch if 35’ requirements met.

*60-minute post hot work designated fire watch if 35’ requirements not met.

Fire watch complete @ 	:

### Fire Watch Requirements and other Considerations

A designated fire watch is required when the 35’ requirement is not met or required by the Fire Department, this shall be an individual whose sole responsibility is to be on guard of potential fires and/or hazards, stopping operations if any hazardous condition is found and is prepared to operate a fire extinguisher in case of a fire and to immediately call 911.

- If detectors (UVIR, Smoke) are covered to prevent alarms, covers must be removed at end of workday.

- If hot works is near ventilation systems coordinate with your Port Construction Inspector.

- Coordinate with Fire Inspector for any hot works on the roof.

- Coordinate with Fire Inspector for any hot works on the ramp.

Hot works in confined space must be coordinated with Port Construction, Safety and Fire Inspectors